Name of Activity/Event: ________________________________________________________________________________________________________________________

| Date: ________________________________________ | Time: ________________________________________ | Venue: _______________________________________ |
| --- | --- | --- |

Before the event

| Time Frame | Task/Duty | Committee In-Charge | Proposed Deadline | Date Completed |
| --- | --- | --- | --- | --- |
| Small/Medium Scale Activity/Event Budget ≤ RM 500 | Large Scale Activity/Event Budget ≥ RM 500 |  |  |  |  |
| 3 – 4 months Before the event date | 7 – 8 months Before the event date | ExCo meeting to decide and approve the activity and elect/appoint organizing committee. |  |  |  |
| 3 – 4 months Before the event date | 7 – 8 months Before the event date | Draft proposal and budget. Sponsorship list + Sponsorship letter VIP list + Invitation letter Publicity materials (Flyer, Poster, Brochure, etc.) Polis permit (for traveling or invitation of outside speakers/judges/performers) (if applicable) |  |  |  |
| 3 months before the event date | 6 months before the event date | Submission of final proposal and budget. (DSA to approve within 5 working days) |  |  |  |
| Book immediately Once the proposal and budget are approved | Book immediately Once the proposal and budget are approved | Venue/Room/Bus/Equipment booking via DSA. (DSA to reply within 5 working days) |  |  |  |
| Book immediately Once the proposal and budget are approved | Book immediately Once the proposal and budget are approved | Book the event date in UTAR President’s/VIP’s diary via DSA. |  |  |  |
| Send immediately Once the proposal and budget are approved | Send immediately Once the proposal and budget are approved | Sponsorship letter sends to potential sponsors. |  |  |  |
| Send immediately Once the proposal and budget are approved | Send immediately Once the proposal and budget are approved | Invitation letter/card sends to VIPs. |  |  |  |
| Invite immediately Once the proposal and budget are approved | Invite immediately Once the proposal and budget are approved | Invitation to First Aid Society for seeking assistant on the event. |  |  |  |
| Once every 2 weeks After the sponsorship letter sent out | Once every 2 weeks After the sponsorship letter sent out | Follow up with potential sponsors. |  |  |  |
| 2 – 3 months Before the event date | 5 – 6 months Before the event date | Publicize the activity/event (After publicity materials are approved by DSA). Distribute flyer/pamphlet/brochure Poster on notice board Booth setup UTAR website announcement (via DSA) UTAR Intranet announcement (portal) (via DSA) UTAR mail master (via DSA) UTAR Facebook announcement (via DSA) Promotional video (if applicable) To liaise with relevant departments to promote the event to public (DCCPR, DPP, CEE and etc) |  |  |  |
| 2 – 3 months Before the event date | 3 – 4 months Before the event date | Application of Advance (to be recorded). |  |  |  |
| 2 – 3 months Before the event date | 2 – 3 months Before the event date | Submission of booklet (after proof-read by English lecturer) to DSA. |  |  |  |
| 1 – 2 months Before the event date | 3 – 6 months Before the event date | Ticket Sale |  |  |  |
| 1 – 2 months Before the event date | 2 – 3 months Before the event date | Submission of program flow with performers/speakers/judges (detailed bio-data if involve outsiders) and description of the performers/talks to DSA. |  |  |  |
| 1 – 2 months Before the event date | 2 – 3 months Before the event date | Invitation letter/card sends to VIPs. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Finalize the item/cash sponsorship. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Follow up and finalize the VIPs’ attendance. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Submission of Emcee Script (after proof-read by English lecturer) to DSA. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Submission of speeches (after proof-read by English lecturer) to DSA. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | VIPs seating arrangement. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Logistic arrangement. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Finalize and submit the number of participants/ticket sold to DSA. |  |  |  |
| 1 – 2 months Before the event date | 1 – 2 months Before the event date | Preparation of refreshment (if applicable). |  |  |  |
| Depend on the committee’s decision | Depend on the committee’s decision | Decoration. |  |  |  |
| Depend on the committee’s decision | Depend on the committee’s decision | Practices & Rehearsal. |  |  |  |
| 1 day Before event date | 1 day Before event date | Final check on facilities, equipments and manpower. |  |  |  |
| 1 day Before event date | 1 day Before event date | Get ready the holding room if involved of VIPs to grace the event. |  |  |  |
| Once the venue handed over to the organiser | Once the venue handed over to the organiser | To check the venue before the event to ensure the condition is in good order by using the “Event Assessment Form” –(FM-DSA-020) |  |  |  |

On the event

| Time Frame | Task/Duty | Committee In-Charge | Proposed Deadline | Date Completed |
| --- | --- | --- | --- | --- |
| Small/Medium Scale Activity/Event Budget ≤ RM 500 | Large Scale Activity/Event Budget ≥ RM 500 |  |  |  |  |
| On the event day itself | On the event day itself | Mark attendance of department concerned & final check of facilities, equipment & manpower. |  |  |  |
| On the event day itself | On the event day itself | Photo taking. |  |  |  |
| On the event day itself | On the event day itself | To tidy up the event venue. |  |  |  |

After the event

| Time Frame | Task/Duty | Committee In-Charge | Proposed Deadline | Date Completed |
| --- | --- | --- | --- | --- |
| Small/Medium Scale Activity/Event Budget ≤ RM 500 | Large Scale Activity/Event Budget ≥ RM 500 |  |  |  |  |
| On the next day of the event day | On the next day of the event day | To check the venue to ensure the condition is in good order after the event by using the “Event Assessment Form” – (FM-DSA-020) |  |  |  |
| Within 1 week After the event date | Within 1 week after the event date | To have post-mortem meeting. Submit post-mortem report to DSA. Submit activity report together with photos to DSA. |  |  |  |
| The day after the event | The day after the event | To return borrowed equipment to DSA. |  |  |  |
| Within 2 weeks After the event date | Within 2 weeks After the event date | Submit income statement together with original receipts to DSA. |  |  |  |

Important notes

- Invitation to Minister/politician/Special Guest must go through President and send out at least 2 months before the event day. Please refer to the Officer In-Charge for the definition of the Special Guest

- Request of message from Minister /politician/Special Guest for booklet purpose and sponsorship for the event must gain approval from President.

- Progressive meeting to be carried out once a week to update the status of each department.

- Meeting to be conducted by the main organizing committee;

- At least 3 times before the event after the proposal and budget are approved (small/medium scale activity/event).

- At least 6 times before the event after the proposal and budget are approved (large scale activity/event).

Monitored by                                                                                                                                  Confirmed by

________________________                                                                                                        _____________________________

Officer In-charge                                                                                                                             HoD, DSA